## Sheet1
| Task No. |  | Product | Code/Software | Matlab Code
Semester 1 | 1 | 1 | Open data | dropView, Matlab | BD_InWater.mat
| 1 | 2 | Data conversion | dropView (for visualization), Matlab | BD_InWater.mat
|  | 2 | Initial data visualization | matlab, dropView | BD_InWater.mat
| 1 | 3 | selection of drop | matlab, dropView | BD_InWater.mat
| 1 | 4 | selection of impact point | matlab | BD_InWater.mat
| 1 | 5 | integration (velocity, depth) | matlab | BD_InWater.mat
| 2 | 6 | soil classification | missing
| 2 | 7 | strain rate correction | matlab | BD_InWater.mat
| 2 | 8 | qsbc | matlab | BD_InWater.mat
| 3 | 9 | pore pressure | matlab
| 4 | 10 | tilt calculator | matlab/excel
Semester 2 | 4 | 11 | Relative density
|  |  | Albatal (2020) | correlation
|  |  | Jaber and Stark (2023) | excel/matlab
| 4 | 12 | friction angle calculation
|  |  | Jaber and Stark (2023) | excel/matlab
|  |  | Albatal (2020) | missing (manual excel coding)
| 4 | 13 | Undrained shear strengths | matlab/excel (sort of)
| 5 | 14 | Pore pressure dissipation | matlab
|  |  | Notes: | 1. Allow user to select what they want as output graphs
2. Allow user to reload previous session or start with new data
3. Allow user to save all data (appopriate file formats?)
4. dropView is a standalone software that only is used for initial data visualization. No processing occurrs within this software
5. User should be allowed to load in blueDrop calibation factors (right now, these are stored as a .pnl file but other formats can be chosen)
|  |  | Product Vision | A UI that integrates all the different processing steps and products.
|  |  | Semester MVP | UI with dedicated tabs that integrates at least (1) and (2)
|  |  | Why? | Need a UI that combines all these processing steps, written in various codes with data in a myriad of formats that are sometimes hard to reproduce
This UI will benefit multiple research efforts around campus: marine energy, sustainable seafood, habitat restoration, erosion characterization
|  |  | Stretch goals | 1. Calculation of duration of impact
2. Averaging of deployments
3. Calculation of parameters based on averaging of deployments or by single deployments.